## Sheet1
Priority | Task | Sub Task | Description | Completed | Progress Notes | Date
H | Cameras | RWS |  | Y
H | Cameras | Mouse scroll |  | Y
H | Cameras | Operator |  | Y
H | Cameras | Vehicle POV |  | Y
H | Environment | Jungle |  | in progress | East Range Gulch height map started
H | GUI | Select payload |  | Y
H | GUI | Pause Menu | Move Buttons to here | N
H | GUI | Main Menu | Select mission, payload, environment, | N
H | Mission | Geo Cache | Collect waypoints, GPS or map views? | N
H | Mission | Resupply | Collect/deliver supplies, timed | N
H | MUV | simplify meshes |  | Y
H | MUV | track w/bones |  | in progress | simplified version completed
H | MUV | Mesh textures |  | Y
H | Payloads | Crows |  | Y
H | Payloads | Side Racks |  | Y
H | Payloads | Front Carrier |  | Y
H | Payloads | Trailer | Loaded | N
H | Payloads | Mulcher | Actually cut trees to clear path | N
H | Payloads | Inflatable Bridge | Inflate, Deploy, Stow | N
H | Payloads | Winch | Stowed Front Carrier too | N
H | RWS Controller | M2 |  | Y
L | Environment | Desert |  | in progress
L | Environment | Snow |  | N
L | Environment | Day/Night |  | Y
L | GUI | Select weapon for RWS |  | N
L | GUI | Select Terrain |  | N
L | MUV | Vehicle Lights |  | Y
L | Other SMET's | MUTT Wheeled |  | N
L | Other SMET's | MUTT Tracked |  | N
L | Other SMET's | Disrupter |  | N
L | Other SMET's | Raider |  | N
L | Payloads | PLRWS |  | N
L | Payloads | COP |  | N
L | Payloads | Flail |  | in progress | Non functional
L | RWS Controller | M-134 |  | N
L | RWS Controller | Mark19 |  | N
L | RWS Controller | 240b |  | N
L | RWS Controller | M149 |  | N
M | Controls | Game pad support |  | Y
M | Controls | MUV Controller Support |  | N
M | Environment | Woods |  | in progress
M | Environment | Urban |  | N
M | GUI | Launch Image/logo |  | in progress | Size is incorrect
M | GUI | Splash Screen |  | N
M | GUI | Pitch/Roll guages |  | in progress | digital readout
M | Mission | Search and Destroy | Hunt/Eliminate Targets, RWS | N
M | Mission | Route plan | Set waypoint/adjust spline, MUV must navigate without rolling | N
M | MUV | Track Noise |  | N
M | MUV | Right | Roll back over naturally | in progress | regen righted +1m up
M | RWS Controller | Shoot |  | in progress
M | RWS Controller | Tracers |  | N
M | RWS Controller | Recoil |  | N
M | RWS Controller | Impact textures |  | N
M | RWS Controller | Impart Force |  | N
M | RWS Controller | Muzzle Blast |  | in progress
M | RWS Controller | Report |  | N
M | RWS Controller | Multi-gun support |  | in progress
M | RWS Controller | Spent Casings |  | in progress